## Sheet1
LOCKEDME.COM AGILE PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE
| LockedMe E-commerce | Winnette Lai | 2022-04-10 | 2022-05-10
| TASK NAME | FEATURE TYPE | CORE CONCEPT | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | RECOMMENDED ENHANCEMENT
Sprint 1
| Feature 1 | Home page display | System out print | 4 | 2022-04-10 | 11 April 2022 | 1 | Completed | Utilisizing java.swing and java.awt for welcome page display
| Feature 1 | User registration | Regex | 4 | 2022-04-11 | 13 April 2022 | 2 | Completed | Add data binding and validation
Sprint 2
| Feature 1 | Add file | createNewFile() | 8 | 14 April 2022 | 18 April 2022 | 4 | Completed | Create button for options with java.swing.JButton , JFileChooser & java.awt.event.ActionEvent;
| Feature 2 | Rename file | renameTo() | 8 | 19 April 2022 | 23 April 2022 | 4 | Completed | Create button for options with java.swing.JButton & java.awt.event.ActionEvent;
| Feature 3 | Delete file | delete() | 8 | 24 April 2022 | 28 April 2022 | 4 | Completed | Create button for options with java.swing.JButton & java.awt.event.ActionEvent;
Sprint 3
| Feature 1 | Search engine | exponentialSearch | 9 | 29 April 2022 | 2022-05-03 | 4 | Completed
| Feature 2 | Sorting | Selection Sort | 9 | 2022-05-04 | 2022-05-08 | 4 | Completed
Sprint 4
| Feature 1 | Return option | history.back() | 7 | 2022-05-09 | 2022-05-10 | 1 | Completed | Create button for options with java.swing.JButton & java.awt.event.ActionEvent;
| Feature 2 | Exit ption | System.exit() | 7 | 2022-05-09 | 2022-05-10 | 1 | Completed | Create button for options with java.swing.JButton & java.awt.event.ActionEvent;